## Work Orders
WO Number | Description | Department | Priority | WO Type | PM | Asset Number | Asset Description | Scheduled Start | Scheduled End | Supervisor | Op Seq | Op Description | Craft/Resource | Est Hours | Depends On Op
WO-10001 | Emergency Feed Pump Repair - Unit 3 | Mechanical | 1 | CM | No | PUMP-301 | Centrifugal Feed Pump 3A | 2026-03-09 | 2026-03-10 | Mike Torres | 10 | Isolate & lock out pump | Mechanic | 1
[11 empty] | 20 | Disconnect motor leads | Electrician | 1.5 | 10
[11 empty] | 30 | Remove pump assembly | Mechanic | 3 | 10
[11 empty] | 40 | Replace impeller & seals | Mechanic | 4 | 30
[11 empty] | 50 | Reinstall pump assembly | Mechanic | 3 | 40
[11 empty] | 60 | Reconnect motor leads | Electrician | 1 | 50
[11 empty] | 70 | Alignment check & test run | Mechanic | 2 | 50,60
WO-10002 | Air Compressor Quarterly PM | Mechanical | 3 | PM | Yes | COMP-110 | Ingersoll Rand Rotary Screw | 2026-03-09 | 2026-03-14 | Mike Torres | 10 | Inspect intake filter | Mechanic | 1
[11 empty] | 20 | Change oil & filter | Mechanic | 1.5
[11 empty] | 30 | Check belt tension & alignment | Mechanic | 1
[11 empty] | 40 | Inspect safety valve | Mechanic | 0.5
[11 empty] | 50 | Test pressure relief | Mechanic | 1 | 40
[11 empty] | 60 | Log readings & close out | Mechanic | 0.5 | 50
WO-10003 | Gearbox Rebuild - Conveyor Drive | Mechanical | 2 | CM | No | GEAR-405 | Falk V-Class Gearbox | 2026-03-09 | 2026-03-14 | Mike Torres | 10 | Remove guards & coupling | Mechanic | 2
[11 empty] | 20 | Drain oil & disconnect | Mechanic | 1 | 10
[11 empty] | 30 | Remove gearbox from base | Mechanic | 3 | 20
[11 empty] | 40 | Disassemble & inspect gears | Mechanic | 4 | 30
[11 empty] | 50 | Replace bearings & seals | Mechanic | 3 | 40
[11 empty] | 60 | Reassemble & set backlash | Mechanic | 3 | 50
[11 empty] | 70 | Reinstall & align | Mechanic | 4 | 60
[11 empty] | 80 | Oil fill & test run | Mechanic | 1.5 | 70
WO-10004 | Overhead Crane Annual Inspection | Mechanical | 3 | PM | Yes | CRANE-01 | 10-Ton Bridge Crane Bay 2 | 2026-03-09 | 2026-03-14 | Mike Torres | 10 | Visual inspection - structure | Mechanic | 2
[11 empty] | 20 | Inspect wire rope & sheaves | Mechanic | 1.5
[11 empty] | 30 | Check brakes & limit switches | Electrician | 2
[11 empty] | 40 | Load test 125% | Mechanic | 3 | 10,20,30
[11 empty] | 50 | Lubricate all points | Mechanic | 1.5 | 40
[11 empty] | 60 | Update inspection log | Mechanic | 0.5 | 50
WO-10005 | Replace Check Valve - Cooling Loop | Mechanical | 4 | CM | No | VALVE-822 | 4-inch Swing Check Valve | 2026-03-11 | 2026-03-14 | Mike Torres | 10 | Isolate & drain section | Pipefitter | 1.5
[11 empty] | 20 | Remove old valve | Pipefitter | 2 | 10
[11 empty] | 30 | Install new valve & gaskets | Pipefitter | 2.5 | 20
[11 empty] | 40 | Pressure test | Pipefitter | 1 | 30
[11 empty] | 50 | Restore system & leak check | Pipefitter | 1 | 40
WO-10006 | Cooling Tower Fan Bearing PM | Mechanical | 3 | PM | Yes | CT-FAN-2 | Cooling Tower Fan Unit 2 | 2026-03-10 | 2026-03-12 | Mike Torres | 10 | Lock out & isolate fan | Mechanic | 0.5
[11 empty] | 20 | Remove fan coupling | Mechanic | 1.5 | 10
[11 empty] | 30 | Replace bearings | Mechanic | 3 | 20
[11 empty] | 40 | Reassemble & align | Mechanic | 2 | 30
[11 empty] | 50 | Test run & vibration check | Mechanic | 1 | 40
WO-10007 | MCC Bucket Replacement - MCC-4B | Electrical | 2 | CM | No | MCC-4B | Motor Control Center 4B | 2026-03-09 | 2026-03-11 | Lisa Chen | 10 | LOTO & verify de-energized | Electrician | 1
[11 empty] | 20 | Remove failed bucket | Electrician | 2 | 10
[11 empty] | 30 | Install new bucket & wire | Electrician | 3 | 20
[11 empty] | 40 | Meggering & continuity test | Electrician | 1.5 | 30
[11 empty] | 50 | Re-energize & test motor | Electrician | 1 | 40
WO-10008 | Transformer Oil Analysis & PM | Electrical | 3 | PM | Yes | XFMR-01 | Main 2000 KVA Transformer | 2026-03-09 | 2026-03-14 | Lisa Chen | 10 | Oil sample collection | Electrician | 1
[11 empty] | 20 | Thermographic scan | Electrician | 1.5
[11 empty] | 30 | Check connections & torque | Electrician | 2
[11 empty] | 40 | Inspect bushings & gaskets | Electrician | 1
[11 empty] | 50 | Test protection relays | Electrician | 2
[11 empty] | 60 | Record readings & report | Electrician | 0.5 | 10,20,30,40,50
WO-10009 | LED Lighting Retrofit - Warehouse B | Electrical | 5 | CM | No | LTNG-WB | Warehouse B Lighting | 2026-03-09 | 2026-03-14 | Lisa Chen | 10 | Survey & mark fixtures | Electrician | 2
[11 empty] | 20 | Remove old HID fixtures (zone 1) | Electrician | 4 | 10
[11 empty] | 30 | Install LED fixtures (zone 1) | Electrician | 4 | 20
[11 empty] | 40 | Remove old HID fixtures (zone 2) | Electrician | 4 | 10
[11 empty] | 50 | Install LED fixtures (zone 2) | Electrician | 4 | 40
[11 empty] | 60 | Test & adjust photocells | Electrician | 1.5 | 30,50
WO-10010 | VFD Preventive Maintenance - AHU-3 | Electrical | 3 | PM | Yes | VFD-AHU3 | ABB ACS880 VFD | 2026-03-10 | 2026-03-11 | Lisa Chen | 10 | Inspect cooling fans & filters | Electrician | 1
[11 empty] | 20 | Check DC bus voltage & capacitors | Electrician | 1.5
[11 empty] | 30 | Meggering motor & cables | Electrician | 1
[11 empty] | 40 | Verify parameter settings | Electrician | 0.5
[11 empty] | 50 | Clean & torque connections | Electrician | 1
WO-10011 | Emergency Generator Monthly PM | Electrical | 2 | PM | Yes | GEN-01 | 500 KW Caterpillar Diesel Gen | 2026-03-09 | 2026-03-10 | Lisa Chen | 10 | Check coolant & oil levels | Mechanic | 0.5
[11 empty] | 20 | Inspect belts & hoses | Mechanic | 0.5
[11 empty] | 30 | Check battery & charger | Electrician | 0.5
[11 empty] | 40 | Load bank test 30 min | Electrician | 1.5 | 10,20,30
[11 empty] | 50 | Transfer switch exercise | Electrician | 1 | 40
[11 empty] | 60 | Log readings & report | Electrician | 0.5 | 50
WO-10012 | Distribution Panel Upgrade - Bldg A | Electrical | 3 | CM | No | PNL-A3 | 208V Distribution Panel A3 | 2026-03-11 | 2026-03-14 | Lisa Chen | 10 | De-energize & LOTO panel | Electrician | 1
[11 empty] | 20 | Remove old breakers | Electrician | 2 | 10
[11 empty] | 30 | Install new breakers & bus | Electrician | 3 | 20
[11 empty] | 40 | Wire & label circuits | Electrician | 2.5 | 30
[11 empty] | 50 | Meggering & test | Electrician | 1.5 | 40
[11 empty] | 60 | Re-energize & verify loads | Electrician | 1 | 50
WO-10013 | Chiller Annual PM - CH-1 | HVAC | 3 | PM | Yes | CH-01 | Trane CenTraVac 500-ton | 2026-03-09 | 2026-03-14 | Robert Kim | 10 | Inspect condenser tubes | HVAC Tech | 3
[11 empty] | 20 | Eddy current test tubes | HVAC Tech | 4 | 10
[11 empty] | 30 | Check refrigerant charge | HVAC Tech | 1.5
[11 empty] | 40 | Inspect & clean evaporator | HVAC Tech | 3
[11 empty] | 50 | Oil analysis & change | HVAC Tech | 2
[11 empty] | 60 | Electrical checks & meggering | Electrician | 2
[11 empty] | 70 | Startup & performance test | HVAC Tech | 2 | 10,20,30,40,50,60
WO-10014 | RTU Compressor Replacement - RTU-7 | HVAC | 3 | CM | No | RTU-07 | Carrier 15-ton Rooftop Unit | 2026-03-10 | 2026-03-14 | Robert Kim | 10 | Recover refrigerant | HVAC Tech | 2
[11 empty] | 20 | Disconnect electrical | Electrician | 1
[11 empty] | 30 | Remove old compressor | HVAC Tech | 3 | 10,20
[11 empty] | 40 | Install new compressor | HVAC Tech | 3 | 30
[11 empty] | 50 | Braze piping & pressure test | HVAC Tech | 2 | 40
[11 empty] | 60 | Reconnect electrical | Electrician | 1 | 40
[11 empty] | 70 | Evacuate & charge system | HVAC Tech | 2 | 50,60
[11 empty] | 80 | Startup & verify operation | HVAC Tech | 1 | 70
WO-10015 | AHU Filter Change - All Units | HVAC | 4 | PM | Yes | AHU-ALL | Air Handling Units 1-6 | 2026-03-09 | 2026-03-11 | Robert Kim | 10 | Replace filters AHU-1 & 2 | HVAC Tech | 2
[11 empty] | 20 | Replace filters AHU-3 & 4 | HVAC Tech | 2
[11 empty] | 30 | Replace filters AHU-5 & 6 | HVAC Tech | 2
[11 empty] | 40 | Check belt tension all units | HVAC Tech | 1.5
[11 empty] | 50 | Verify static pressure readings | HVAC Tech | 1 | 10,20,30
WO-10016 | Cooling Tower Annual PM | HVAC | 3 | PM | Yes | CT-01 | BAC Cooling Tower 200-ton | 2026-03-10 | 2026-03-14 | Robert Kim | 10 | Clean basin & strainers | HVAC Tech | 3
[11 empty] | 20 | Inspect fill media | HVAC Tech | 1.5
[11 empty] | 30 | Check spray nozzles | HVAC Tech | 1
[11 empty] | 40 | Inspect drift eliminators | HVAC Tech | 1
[11 empty] | 50 | Water treatment check | HVAC Tech | 1
[11 empty] | 60 | Test conductivity controls | HVAC Tech | 0.5 | 50
WO-10017 | Pressure Transmitter Cal - Boiler | Instrumentation | 3 | PM | Yes | PT-BLR | Rosemount 3051 Transmitters | 2026-03-09 | 2026-03-11 | Lisa Chen | 10 | Calibrate PT-101 thru PT-105 | Instrument Tech | 4
[11 empty] | 20 | Calibrate PT-106 thru PT-110 | Instrument Tech | 4
[11 empty] | 30 | Verify control loops respond | Instrument Tech | 2 | 10,20
[11 empty] | 40 | Update calibration records | Instrument Tech | 1 | 30
WO-10018 | Flow Meter Replacement - FT-220 | Instrumentation | 2 | CM | No | FT-220 | Endress+Hauser Promag | 2026-03-09 | 2026-03-10 | Lisa Chen | 10 | Isolate process line | Instrument Tech | 1
[11 empty] | 20 | Remove failed transmitter | Instrument Tech | 1.5 | 10
[11 empty] | 30 | Install new transmitter | Instrument Tech | 2 | 20
[11 empty] | 40 | Configure & calibrate | Instrument Tech | 1.5 | 30
[11 empty] | 50 | Verify DCS signal & trend | Instrument Tech | 1 | 40
WO-10019 | SIS Proof Test - Shutdown Valves | Instrumentation | 2 | PM | Yes | SIS-01 | Safety Instrumented System | 2026-03-11 | 2026-03-14 | Lisa Chen | 10 | Proof test SDV-101 | Instrument Tech | 2
[11 empty] | 20 | Proof test SDV-102 | Instrument Tech | 2
[11 empty] | 30 | Proof test SDV-103 | Instrument Tech | 2
[11 empty] | 40 | Verify logic solver response | Instrument Tech | 2 | 10,20,30
[11 empty] | 50 | Document test results | Instrument Tech | 1 | 40
WO-10020 | Level Transmitter Annual Cal | Instrumentation | 4 | PM | Yes | LT-TANK | Tank Farm Level Transmitters | 2026-03-09 | 2026-03-14 | Lisa Chen | 10 | Calibrate LT-301 thru LT-304 | Instrument Tech | 3
[11 empty] | 20 | Calibrate LT-305 thru LT-308 | Instrument Tech | 3
[11 empty] | 30 | Verify alarm setpoints | Instrument Tech | 1.5 | 10,20
[11 empty] | 40 | Update cal certs | Instrument Tech | 1 | 30
WO-10021 | Roof Leak Repair - Bldg C | Facilities | 4 | CM | No | BLDG-C | Building C - Main Plant | 2026-03-09 | 2026-03-14 | Robert Kim | 10 | Locate & mark leak sources | Facilities Tech | 2
[11 empty] | 20 | Remove damaged flashing | Facilities Tech | 3 | 10
[11 empty] | 30 | Install new membrane & flashing | Facilities Tech | 4 | 20
[11 empty] | 40 | Seal & waterproof test | Facilities Tech | 2 | 30
WO-10022 | Fire Suppression System Annual PM | Facilities | 2 | PM | Yes | FIRE-01 | Wet Pipe Sprinkler System | 2026-03-09 | 2026-03-11 | Robert Kim | 10 | Visual inspection all heads | Facilities Tech | 3
[11 empty] | 20 | Flow test main drain | Facilities Tech | 1
[11 empty] | 30 | Inspect fire pump & jockey | Mechanic | 1.5
[11 empty] | 40 | Test alarm panel & devices | Electrician | 2
[11 empty] | 50 | Trip test & full flow | Facilities Tech | 2 | 10,20,30,40
[11 empty] | 60 | Update inspection tags | Facilities Tech | 0.5 | 50
WO-10023 | Loading Dock Door #3 Repair | Facilities | 3 | CM | No | DOCK-03 | Overhead Door - Dock 3 | 2026-03-10 | 2026-03-12 | Robert Kim | 10 | Inspect tracks & rollers | Facilities Tech | 1
[11 empty] | 20 | Replace damaged panels | Facilities Tech | 3 | 10
[11 empty] | 30 | Adjust springs & tension | Facilities Tech | 2 | 20
[11 empty] | 40 | Test motor & controls | Electrician | 1 | 30
[11 empty] | 50 | Lubricate & test full cycle | Facilities Tech | 1 | 40
WO-10024 | Emergency Eyewash & Shower PM | Facilities | 2 | PM | Yes | EW-ALL | Plant Eyewash Stations | 2026-03-09 | 2026-03-10 | Robert Kim | 10 | Flush & test stations 1-10 | Facilities Tech | 3
[11 empty] | 20 | Flush & test stations 11-20 | Facilities Tech | 3
[11 empty] | 30 | Replace damaged parts | Facilities Tech | 2 | 10,20
[11 empty] | 40 | Verify water temp & flow | Facilities Tech | 1 | 30
[11 empty] | 50 | Update compliance log | Facilities Tech | 0.5 | 40

## Employees
Employee Name | Department | Craft/Resource | Hours Per Day | Supervisor | Skills
James Wilson | Mechanical | Mechanic | 8 | Mike Torres | pumps, rotating equipment, alignment, rigging, welding
Carlos Ruiz | Mechanical | Mechanic | 8 | Mike Torres | welding, fabrication, pumps, compressors, conveyors
David Park | Mechanical | Mechanic | 8 | Mike Torres | cranes, conveyors, gearboxes, bearings, lubrication
Kevin Moore | Mechanical | Pipefitter | 8 | Mike Torres | pipe fitting, welding, valves, steam systems, pressure testing
Brian Scott | Mechanical | Pipefitter | 8 | Mike Torres | pipe fitting, pressure testing, gaskets, flanges, threading
Angela Davis | Electrical | Electrician | 8 | Lisa Chen | motors, MCCs, transformers, LOTO, medium voltage
Marcus Hall | Electrical | Electrician | 8 | Lisa Chen | VFDs, PLCs, power distribution, generators, lighting
Steve Adams | Electrical | Electrician | 8 | Lisa Chen | lighting, conduit, wiring, panels, troubleshooting, controls
Rachel Green | Electrical | Instrument Tech | 8 | Lisa Chen | transmitters, calibration, DCS, SIS, analyzers
Tony Nguyen | Electrical | Instrument Tech | 8 | Lisa Chen | flow meters, analyzers, control valves, PLC, SCADA
Jeff Martinez | HVAC | HVAC Tech | 8 | Robert Kim | chillers, refrigeration, air handling, DDC controls
Pete Collins | HVAC | HVAC Tech | 8 | Robert Kim | RTUs, split systems, ductwork, refrigerant recovery, brazing
Sam Butler | HVAC | HVAC Tech | 8 | Robert Kim | boilers, cooling towers, pumps, piping, water treatment
Dan Murphy | Facilities | Facilities Tech | 8 | Robert Kim | roofing, painting, carpentry, general maintenance, plumbing
Chris Evans | Facilities | Facilities Tech | 8 | Robert Kim | plumbing, fire protection, doors, locks, grounds, eyewash

## Instructions
eAM Scheduler — Template Instructions
WORK ORDERS SHEET
This sheet contains your work orders and their operations (tasks).
Required Columns:
WO Number — Unique work order identifier (e.g. WO-10001)
Op Seq — Operation sequence number within the WO (e.g. 10, 20, 30)
Op Description — What the operation involves
Craft/Resource — Trade or resource type needed (Mechanic, Electrician, etc.)
Est Hours — Estimated hours to complete the operation
Recommended Columns:
Description — Work order description
Department — Organizational department (Mechanical, Electrical, HVAC, etc.)
Priority — 1=Emergency, 2=Urgent, 3=High, 4=Medium, 5=Low
WO Type — PM (Planned Maintenance) or CM (Corrective Maintenance)
PM — Yes or No flag for planned maintenance
Asset Number — Equipment tag number
Asset Description — Equipment description
Scheduled Start — Target start date (YYYY-MM-DD)
Scheduled End — Target completion date (YYYY-MM-DD)
Supervisor — Responsible supervisor or planner
Depends On Op — Comma-separated list of predecessor op sequences (e.g. "10,20")
Format Notes:
- WO-level fields (Description, Dept, etc.) only need to be on the first op row
- Subsequent ops for the same WO can leave WO-level columns blank
- Column names are matched flexibly — the scheduler auto-detects them
- PM flag accepts: Yes, Y, 1, True, PM
- Departments and crafts are auto-discovered from your data
EMPLOYEES SHEET
This sheet lists your available workforce.
Required Columns:
Employee Name — Full name
Craft/Resource — Must match craft names used in Work Orders
Recommended Columns:
Department — Must match department names in Work Orders
Hours Per Day — Available hours (default: 8)
Supervisor — Reporting supervisor
Skills — Comma-separated skill list (used by AI scheduler for matching)
PM SCHEDULING PRIORITY
- PM work orders are auto-prioritized above CM at the same priority level
- The auto-scheduler fills PM work first within their date windows
- PM compliance is tracked separately in the Executive Summary